## FY19-22 KAUAI SURVEY
DEPARTMENT OF TRANSPORTATION ¦ STATEWIDE TRANSPORTATION IMPROVEMENT PROGRAM (STIP)
FFY 2019 THRU FFY 2022 (FFY 2023-2024 Informative Only) D R A F T UNCONSTRAINED
Revision Effective Date: April 19, 2018
Project Criteria Color Key: GREEN = System Preservation PURPLE = Safety Improvements BROWN = Congestion Mitigation
PINK = Modernization ORANGE = Enhancement BLUE = Human Services Transportation Program TURQUOISE = Transit
| PROJECT |  |  | FFY2019 (10/1/18 - 9/30/19) | FFY2020 (10/1/19 - 9/30/20) | FFY2021 (10/1/20 - 9/30/21) | FFY2022 (10/1/21 - 9/30/22) | FFY2023 (10/1/22 - 9/30/23) | FFY2024 (10/1/23 - 9/30/24) | RANK IN ORDER OF: H - High M - Medium L -Low PRIORITY
|  |  |  | TOTAL | TOTAL | TOTAL | TOTAL | TOTAL | TOTAL
|  |  | PHASE | (x$1000) | (x$1000) | (x$1000) | (x$1000) | (x$1000) | (x$1000)
KAUAI : STATE - FHWA
| KS1. | Bridge and Pavement Improvement Program, Kauai
| SysPres |  | CON | 8500 | 8500 | 8500 | 8500 | 8500 | 8500
Estimated Total Project Cost - $67,200,000 --System maintenance of highway bridges and pavements. Work may include bridge
and/or pavement reconstruction, resurfacing, restoration, rehabilitation and/or preservation. Yearly lump sum amounts represent
total State Special Maintenance Program (SMP) funding levels anticipated for Kauai program. The SMP is a program that funds
individual repair or maintenance projects that do not normally occur annually. SMP funds have funded resurfacing and pavement
and bridge preservation projects (System Preservation). The current list of prioritized proposed SMP projects has been posted
on the STIP website at: http://hidot.hawaii.gov/highways/other/other-related-links/stip/.
Qualified and priority SMP projects could receive federal funds should they become available.
| KS2. | Guardrail and Shoulder Improvements on State Highways, Kauai
| Safety | Part 5 | PE1
|  |  | PE2 | 50
|  |  | CON | 2000
|  | Part 6 | PE |  | 500
|  |  | CON |  |  | 2000
|  | Part 7 | PE |  |  |  | 500
|  |  | CON |  |  |  |  | 2000
Estimated Total Project Cost - $3,300,000 -- Improve guardrails and shoulders at various locations.
| KS3. | Kapule Highway / Rice Street / Waapa (RTE 51) Road, Improvements and Nawiliwili Bridge Replacement
| SysPres |  | CON |  | 6000
Estimated Total Project Cost - $5,440,000 -- Strengthen/widen existing Nawiliwili Bridge. Implement drainage improvements
and safety improvements including new signing and striping and guardrails. Improve roadway approach to the bridge.
| KS5. | Kaumualii Highway (RTE 50), Bridge Replacement, Omao Bridge
| SysPres |  | CON |  |  | 15000
|  |  | ADVCON |  |  |  | 0
Estimated Total Project Cost - $8,000,000 -- Rehabilitation of concrete T-girder bridge on Kaumualii Hwy
in the vicinity of Omao Road.
| KS6. | Kuhio Highway (RTE 56), Bridge Replacement, Kapaia Bridge
| SysPres |  | CON |  | 11275
|  |  | ADVCON |  |  | 0
Estimated Total Project Cost - $13,000,000 -- Replacement of a multi-T beam reinforced concrete girder on Kuhio Hwy
in the vicinity of Kapaia.
| KS7. | Kuhio Highway (RTE 560), Bridge Rehabilitation, Wainiha Stream Bridges #1, #2, #3, Phase 2 - Bridge work
| SysPres |  | CON | 30000
Estimated Total Project Cost - $25,300,000 -- Repair/rehabilitate existing bridges. 2015 CON funds to procure a Construction
Management General Contractor (CMGC) to provide construction related input as the designer prepares the designs.
| KS8. | Kuhio Highway (RTE 560), Bridge Rehabilitation, Waioli, Waipa, and Waikoko Stream Bridges
| SysPres |  | ROW | 630
Phase 2 - Bridge work
|  |  | CON |  |  | 12000
Estimated Total Project Cost - $11,000,000 -- Rehabilitate existing bridges.
| KS9. | Kuhio Highway (RTE 56), Bridge Repair, Hanalei Bridge
| SysPres |  | CON | [5 empty] | 6000
Estimated Total Project Cost - $6,500,000 - Replace remove and replace deteriorated steel as well as the
deteriorated paint system on this historic bridge.
| KS10. | Kuhio Highway (RTE 56), Bridge Repair, Wailua River Bridge
| SysPres |  | CON | [5 empty] | 4000
Estimated Total Project Cost - $4,500,000 - Replace deteriorated steel supports and all bearing areas of the bridge.
Replace deteriorated concrete as well as bearings.
| KS11. | Kuhio Highway (RTE 56) Emergency Slope Stabilization, Kalihiwai Bridge
| SysPres |  | ADVCON | 0 | 0
Estimated Total Project Cost - $15,000,000 - Slope stabilization including clearing trees, removing loose rocks,
installing rock anchors and installing shielding for motorists.
| KS12. | Kuhio Highway (RTE 56) Improvements, Kapaa Solutions (Priority #2),
| Modern | Vicinity of Kapule Highway to Vicinity of Wailua Bridge
|  |  | PE1 |  | 750
|  |  | PE2 |  |  | 1125
|  |  | ROW |  |  |  | 18200
|  |  | CON |  |  |  |  | 21500
Estimated Total Project Cost - $45,000,000 - The purpose of this project is to reduce congestion
and improve mobility in the Kapaa area.
| KS13. | Kuhio Highway (Route 56), Short Term Improvements, Kuamoo Road to Temporary Bypass Road
| Congest |  | ADVCON | 0 | 0
|  |  | ADVCON | 0 | 0
Estimated Total Project Cost - $20,000,000 -- Improvements to Kuhio highway likely to include but are not limited to,
repaving, widening the roadway to accomdate a new southbound lane, improving operating conditions of existing
intersections, and improving existing auxiliary turn lanes.
| KS14. | Kuhio Highway (RTE 56) Traffic Signal Optimization and Intersection Improvements, Kapaa Solutions (Priority #3)
| Congest |  | CON |  | 1480
Estimated Total Project Cost - $2,000,000 - Improve intersection operations in order to provide additional capacity.
1 | KS15. | National Recreational Trails Program - Kauai (DLNR)
| Enhance |  | CON | 314 | 314 | 314 | 314 | 314 | 314
Estimated Total Project Cost - $1,900,000 -- A Federal-aid assistance program to help the State provide and maintain
recreational trails for both motorized and non-motorized recreational use. Anticipated funding for Kauai program.
| KS16. | Waimea Canyon Drive/Kokee Road Improvements, Phase 2A (MP 4-8)
| Safety |  | CON |  |  |  | 5000
Estimated Total Project Cost - $5,500,000 - Improvements include constructing paved shoulders,
installing guardrails, pavement markings, signs and other improvements.
| KAUAI : STATE - FHWA TOTAL |  |  | 41494 | 28819 | 38939 | 32514 | 32314 | 18814
COUNTY OF KAUAI - FHWA
| KC1. | Anini Bridge #2 Replacement
| SysPres |  | DES |  | 500
|  |  | CON | [5 empty] | 3000
Estimated Total Project Cost - $3,500,000 -- Replace existing double box culvert and temporary one-lane precast
panel bridge with a new structure. Demolish existing bridge, construct temporary bypass bridge, construct new
two-lane bridge and possibly paved shoulders; relolcate utilities.
| KC2. | Bridge Inspection and Appraisal
| SysPres |  | OPR |  | 125 |  | 125 |  | 125
Estimated Total Project Cost - $375,000 -- Inspection of various bridges throughout the County. FHWA Requirement.
This is a regularly scheduled program.
| KC3. | Haleko Road (Route 5040) Improvements
| SysPres |  | DES |  |  | 400
|  |  | CON | [5 empty] | 3000
Estimated Total Project Cost - $3,400,000 -- Project Limits are full length of Haleko Road; Resurface and Reconstruct
pavement as needed; widen roadway to construct on-road bike lanes, construct a sidewalk on one side of the road where
no sidewalk exists; add crosswalks as needed to service new sidewalk; add/improve turn lanes as needed.
| KC4. | Hanapepe Road (Rte 545) Resurfacing
| SysPres |  | CON |  | 3900
Estimated Total Project Cost - $3,200,000 -- Resurface the entire length (5400 feet) of Hanapepe Road. Full depth
reclamation (FDR) technology will be used on this project whenever necessary to match existing adjacent facilities.
| KC5. | Improvements to Maluhia Rd. (RTE 520) and Kōloa Rd. (RTE 530)
| SysPres |  | ADVCON | 0
Estimated Total Project Cost - $13,000,000 -- Part of an ongoing roadway and street maintenance program.
Work proposed for this phase will involve rehabilitation and resurfacing of the pavement of Maluhia Road and Koloa
Road, hich exhibit cracked and delaminated pavement as well as base failure. The work also includes shoulder widening
these roads, to better serve all users and provide support for the pavement. The work also includes drainage
improvements in areas that exhibit erosion and inadequate drainage.
| KC6. | Kamalu Road (Route 581) Improvements
| SysPres |  | DES |  |  |  | 900
|  |  | CON | [5 empty] | 6000
Estimated Total Project Cost - $6,900,000 -- Resurface pavement (and Reconstruct as needed) the full length of
Kamalu Road; widen roadway to provide paved shoulders, 5 feet wide where feasible; replace one-lane bridge at Kalama
Stream with a two-lane bridge with appropriate bridge railing and approach guardrail; construct other safety improvements.
| KC7. | Kawaihau Road (Route 5860) Improvements
| SysPres |  | DES |  |  | 600
|  |  | CON | [5 empty] | 5000
Estimated Total Project Cost - $5,600,000 -- Project Limits are from Hauaala Road to Ka‘apuni Road and Kapahi Park -
The project includes construction of the following: pavement resurfacing and reconstruction; widened and/or new
sidewalks; shoulder widening; intersection improvements including left turn lanes and crosswalks.
| KC8. | Kawaihau Road (Route 5860), Hauaala Road (Route 5865), Mailihuna Road (Route 5870),
| Safety | Complete Street & Safety Improvements
|  |  | CON | 3183
Estimated Total Project Cost - $3,435,000 -- Construction of roundabouts at Hauaala Rd (Route 5865)/Kawaihau Rd (Route 5860)/
Mailihuna Rd (Route 5870) Intersection; Sidewalk and pedestrian crossing improvements on Kawaihau Rd (Route 5860); Sidewalk
construction on Hauaala Rd (Route 5865) in the vicinity of Saint Catherine School; Roundabout at Kawaihau Rd (Route 5860)/
Nunu Rd intersection; Sidewalk construction on Mailihuna Rd (Route 5870); Bus stop shelters on Kawaihau Rd (Route 5860).
| KC9. | Kekaha Road (Route 551) Improvements
| SysPres |  | DES |  |  | 800
|  |  | CON |  |  |  |  | 5000
Estimated Total Project Cost - $5,800,000 -- Project Limits Kaumuali‘i Highway to Amakihi Street -- Resuface
pavement (and Reconstruct as needed); construct shared use path on mauka side (1.8 miles); reconstruct
broken sidewalks and add additional sidewalks on the makai side.
| KC10. | Kilauea Road and Kolo Road (Route 562) Resurfacing and Multi-Modal Access
| SysPres |  | PE2 | 350
|  |  | CON |  |  | 9000
Estimated Total Project Cost - $9,680,000 -- The project includes construction of the following: pavement resurfacing
and reconstruction; new sidewalks and sidewalk repair; new crosswalks; widening and extension of a shared use path;
shoulder widening; intersection improvements including a mini-roundabout at the Kolo Road/Kilauea Road intersection.
| KC11. | Lihue-Anahola Coastal Bike Path
| Enhance | Phase III - Lydgate Park to Kapaa Bike/Pedestrian Path, Phase C & D
|  |  | CON | 1091
A shared-use path for pedestrians, bicyclists, and other users from Papaloa Road to Uhelekawawa Canal, a distance
of approximately 1.2 miles . The bike/pedestrian path will be 10 to 12 feet wide and allow movement in both directions.
Phase IV - Ahukini to Lydgate Park Bike/Pedestrian Path, Phase A - Ahukini Landing to Hanamaulu Beach Park
|  |  | ROW | 100
|  |  | PE2 |  | 1179
|  |  | CON |  |  |  |  | 8041
Phase IV - Ahukini to Lydgate Park Bike/Pedestrian Path, Phase B - Hanamaulu Beach Park to Wailua Golf Course
|  |  | ROW | 100
|  |  | PE2 |  | 840
|  |  | CON |  |  |  | 4288
The 10' to 12' wide 6' thick 5.3 mile concrete path from Ahukini Pt., connecting with an existing path at Lydgate Park.
A future phase C will go from Wailua Golf Course to Lydgate Park and cost $9.5 million.
Phase VI - Nāwiliwili to Ahukini Bike/Pedestrian Path, Phase A - Ninini Point to Ahukini
|  |  | PE2 |  |  |  | 1945
|  |  | ROW |  |  |  | 424
|  |  | CON | [5 empty] | 4500
Phase VI - Nāwiliwili to Ahukini Bike/Pedestrian Path, Phase B - Ninini Point to Nawiliwili Beach Park
|  |  | PE2 |  |  |  |  | 1061
Path development will consist of a 10 to 12-foot wide concrete shared-use coastal path constructed of various low-maintenance materials. Bike
lane and sidewalk improvements to existing and planned street corridors will provide additional connectivity through urban areas.
Estimated Total Project Cost - $50,500,000 -- Complete Lihue - Anahola Coastal Bike Path, a shared use path.
| KC12. | Moi Road (Route 543) Resurfacing and Sidewalks
| SysPres |  | DES |  |  | 300
|  |  | CON |  |  |  |  | 3500
Estimated Total Project Cost - $3,800,000 -- Resuface and reconstruct pavement as needed, along the full length of Moi Road;
construct sidewalk on the east side where there is no sidewalk; add shoulders both sides between Kaumuali‘i Highway and Kane St.
| KC13. | Olohena Road (RTE 581), Kukui Street (RTE 581), and Ulu Street (RTE 5805) Improvements
| SysPres |  | CON | 7000
|  |  | ADVCON |  | 0
Estimated Total Project Cost - $7,700,000 -- The project includes construction of the following: rehabilitation and
resurfacing of the pavement of the project roads, which exhibit cracked and delaminated pavement as well as base
failure. The work also includes shoulder widening on Kukui Street and Olohena Road where feasible, to better serve
all users and provide support for the pavement. Between Kuhio Highway and the Kapaa Bypass, is proposed on
one side, and the proposed paved shoulders are intended to be marked as bicycle lanes. The work also includes
drainage improvements in areas that exhibit erosion and inadequate drainage.
| KC14. | Poipu Road (Route 520) Multimodal Improvements, Phase 1 - Lawai Road to Keleka Road
| Enhance |  | CON |  | 5200
Poipu Road (Route 520) Multimodal Improvements, Phase 2 - Koloa Road to Lawai Road
|  |  | CON |  |  | 4080
Estimated Total Project Cost - $9,500,000 -- Construction of sidewalks and bike lanes; Intersection and pedestrian
crossing improvements; Construction of a roundabout at Kiahuna Plantation Drive intersection and Ala Kinoiki;
Construction of bus stop shelters; Construction of medians and landscaping
| KC15. | Puhi Road (Route 5010) Rehabilitation, Phase 2 - Kaneka Street to S. Haleukana Street (MP 0.35 to 0.80)
| SysPres |  | CON |  |  |  | 3714
Estimated Total Project Cost - $7,100,000 -- Rehabilitate Puhi Road. Phase 1 was from Kaumualii Hwy (MP 0.00) to
Kaneka St. Phase 2 will rehabilitate Puhi Road from Kaneka Street to South Haleukana Street intersection (MP 0.35 to
MP 0.80), pavement widening, incorporating Complete Streets principles, and replacing pavement markers, striping, and traffic signs.
| KC16. | Waimea to Kekaha Shared Use Path, Phase I
| Enhance |  | PE2 |  | 400
|  |  | CON |  |  |  | 2000
Estimated Total Project Cost - $4,500,000 -- Construction of a Shared Use Path along the mauka side of Kaumualii
Highway, between Carl Furutani Street in Waimea and Alae Road in Kekaha. Phase II of the path is proposed to
be constructed along with Kekaha Road improvements.
| COUNTY OF KAUAI - FHWA TOTAL |  |  | 11824 | 12144 | 15180 | 13396 | 17602 | 21625
COUNTY OF KAUAI - FTA
| KC17. | Bus and Bus Facility
| Transit |  | EQP | 590 | 609 | 627 | 646
Estimated Total Project Cost - $3,400,000 -- Capital projects to replace, rehabilitate and purchase buses, vans,
and related equipment, and to construct bus-related facilities.
| KC18. | Rural Transportation Program
| Transit |  | OPR | 2298 | 2368 | 2440 | 2514
Estimated Total Project Cost - $13,160,000- -- Planning, capital, operating, job access and
reverse commute projects, and the acquisition of public transportation services.
| COUNTY OF KAUAI - FTA TOTAL |  |  | 2888 | 2977 | 3067 | 3160 | 0 | 0
Thank you for completing this survey. Your input helps to inform us about transportation issues that
are important to you, the public.
Please return this form to us at the end of the night or mail it or fax it to:
| Email: hwy.stip.projects@hawaii.gov |  |  |  |  | Fax: 808-587-1787
Hawaii Department of Transportation
Highways Division
869 Punchbowl Street, Room 301
Honolulu, Hawaii 96813
Attn: 19-22 STIP Survey
The Microsoft Excel file of this form is posted on our website:
http://hidot.hawaii.gov/highways/other/other-related-links/stip/
PLEASE COMPLETE AND RETURN THIS FORM BY MONDAY, JUNE 18, 2018.